## Slide 2: Greenfield
Overview:
  Our current endpoint detection and response tool is going end of life in July 2024. After reviewing options, we have down selected SentinelOne to replace both Carbon Black and Cylance. SentinelOne will provide more defensive capabilities with a lower management requirement.
  Phases:
  Phase 1: Install SentinelOne in detect only mode on all machines and servers
  Phase 2: Turn on protect mode for SentinelOne. Remove Cylance
  Current Blockers:
  Palo Alto VPN HIP configuration
  Conversation with Chris on dates. Might need to renew Cylance
  CR approval
  Risks:
  Server install might cause delay
  Finding malware, we are not aware of
Macs taking longer than 1 month(scheduling)
Server diversity each type of server may react differently
Key Dates:
Cylance expiration: July 16th
Carbon Black Response expiration: June 28th

## Slide 3: Greenfield Timeline
Blockers:
CyberGRX questionnaire approval
Wiz signoff, resourcing, and implementation
Decision on solution for Brownfield to Greenfield communication (refer to deck XX)
Resourcing (refer to slide XX for ENG priorities)
Risks:
Lack of resourcing and skillset with Jagadish’s departure
Complete
1 month
1 month
XXX
XXX
XXX
Phase 1 (Nova)
Build Greenfield (pre-prod)
  Natilik contract negotiations
  Design workshops and reviews
  Creation of dev environment
  Build production replica
  ELZ deployment into pre-prod for 4 regions
Phase 1.1
  Greenfield Signoff (prod)
  Architecture review
  Security review
  CyberGRX questionnaire
  Wiz signoff and implementation
Phase 1.2
  Connect Greenfield to Brownfield
  Documentation
  Add resources in pre-prod
  Staging in pre-prod
  Connect to Brownfield
  Implement solution for communication between DCs on the hosted data centers
  Deploy resources from pre-prod to prod
  CR-3051: pre-prod
  CR-3071, 3182, 3198: connecting pre-prod to prod
Phase 1.3
  Expansion of domain controller
  Create and replicate 8 new DCs across the region
  Configure Azure DR for primary region (site recovery)
Phase 1.4
  Migration prep
  Create new AD sync servers
  Create new Okta sync servers
  Create new PMP servers and PMP clean up (entitlements)
  Create additional Azure Migrate projects for each region
Phase 3
  Server migration
  Technology servers
XXX
Phase 4
  Long-term goals
  Azure RBAC testing in dev
  Build a Splunk forwarder in the new DMZ
  New Splunk log server
  Additional Azure policies for Compliance/audit

## Slide 4: Greenfield Phase 1 Breakdown
June 7th
June 10th
June 17th
June 20th
June 24th
June 27th
Phase 1 (Nova)
Build Greenfield (pre-prod)
      Natilik contract negotiations
      Natilik build
Phase 1.1
  Greenfield Signoff
    Architecture review
    Security review
    CyberGRX questionnaire
    Wiz implementation
Phase 1.2
  Connect Greenfield to Brownfield
    Restructuring
    Servers(mix of critical and noncritical)
Phase 1.3
  Expansion of domain controller
    Park Hill
    Camberview
    Servers(mix of critical and noncritical)
Phase 2
  Migration prep
  Turn on Sentinel One to protect mode for all
  Removal Cylance
Phase 3
  Migration
  Removal of Cylance
CRs
CRs
CRs
Blockers:
CyberGRX questionnaire approval
Wiz implementation
Risks:
Lack of resourcing and skillset with Jagadish’s departure
CRs
CRs
CRs

## Slide 5: ENG work as it relates to Greenfield
June 7th
June 10th
June 17th
June 20th
June 24th
June 27th
Phase 1.1
  Install Sentinel One for:
      Corp
      Mgmt.
      Macs
      Technology
      Servers (mix of critical and non-critical)
  Disable tamper protection on Cylance
Phase 1.2
  Install Sentinel One for
    Advisory
    Servers(mix of critical and noncritical)
  Disable tamper protection on Cylance
Phase 1.3
  Install Sentinel One for:
    Restructuring
    Servers(mix of critical and noncritical)
  Disable tamper protection on Cylance
Phase 1.4
  Install Sentinel One for:
    Park Hill
    Camberview
    Servers(mix of critical and noncritical)
  Disable tamper protection on Cylance
Phase 2.1
  Turn on Sentinel One to protect mode for all
  Removal Cylance
Phase 2.2
  Removal of Cylance
CR1 –Install Sentinel One in detect/audit mode and remove Bit9 and Carbon Black Response
CR1 –Install Sentinel One in detect/audit mode and remove Bit9 and Carbon Black Response
CR1 –Install Sentinel One in detect/audit mode and remove Bit9 and Carbon Black Response
CR1 –Install Sentinel One in detect/audit mode and remove Bit9 and Carbon Black Response
CR2 -Disable the tamper protection on Cylance
CR3- Removal of Cylance and Enforce Sentinel One
Blockers:
CyberGRX questionnaire approval
Wiz implementation
Risks:
Lack of resourcing and skillset with Jagadish’s departure

## Slide 6
Appendix